## Cover
Project Plan
Generated: | April 07, 2026
Solution: | Intelligent Document Processing
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | Project Manager | Not Started
Discovery | Document Analysis & Classification Requirements | 5 days | [START_DATE+1] | [START_DATE+6] | Project Kickoff | Business Analyst | Not Started
Discovery | AWS AI Services Assessment (Textract/Comprehend/A2I) | 5 days | [START_DATE+3] | [START_DATE+8] | Project Kickoff | Solution Architect | Not Started
Discovery | Data Privacy & Compliance Review | 5 days | [START_DATE+5] | [START_DATE+10] | Document Analysis | Security Architect | Not Started
Discovery | Sample Document Collection | 4 days | [START_DATE+6] | [START_DATE+10] | Document Analysis | Business Analyst | Not Started
Planning | IDP Solution Architecture Design | 7 days | [START_DATE+10] | [START_DATE+17] | AWS Assessment | Solution Architect | Not Started
Planning | Data Flow & API Design | 5 days | [START_DATE+12] | [START_DATE+17] | Architecture Design | Technical Lead | Not Started
Planning | Security Architecture & IAM Design | 5 days | [START_DATE+14] | [START_DATE+19] | Architecture Design | Security Architect | Not Started
Planning | Infrastructure & Cost Planning | 4 days | [START_DATE+15] | [START_DATE+19] | Architecture Design | Cloud Architect | Not Started
Build | AWS Infrastructure Provisioning | 7 days | [START_DATE+19] | [START_DATE+26] | Infrastructure Planning | DevOps Engineer | Not Started
Build | S3 Buckets & DynamoDB Setup | 4 days | [START_DATE+22] | [START_DATE+26] | Infrastructure Provisioning | DevOps Engineer | Not Started
Build | Lambda Functions & Step Functions Setup | 10 days | [START_DATE+26] | [START_DATE+36] | S3 Setup | Backend Developer | Not Started
Build | API Gateway & Authentication Setup | 6 days | [START_DATE+28] | [START_DATE+34] | Lambda Setup | Backend Developer | Not Started
Build | Amazon Textract Integration | 8 days | [START_DATE+34] | [START_DATE+42] | Lambda Functions | Technical Lead | Not Started
Build | Amazon Comprehend Integration | 6 days | [START_DATE+38] | [START_DATE+44] | Textract Integration | Technical Lead | Not Started
Build | Amazon A2I Human Review Setup | 7 days | [START_DATE+42] | [START_DATE+49] | Comprehend Integration | Technical Lead | Not Started
Build | Document Processing Pipeline | 10 days | [START_DATE+36] | [START_DATE+46] | API Gateway Setup | Backend Developer | Not Started
Build | Web Interface Development (Optional) | 10 days | [START_DATE+42] | [START_DATE+52] | API Gateway Setup | Frontend Developer | Not Started
Build | CloudWatch Monitoring & Alerting | 5 days | [START_DATE+46] | [START_DATE+51] | Processing Pipeline | DevOps Engineer | Not Started
Test | Unit Testing & Code Coverage | 7 days | [START_DATE+46] | [START_DATE+53] | Processing Pipeline | Development Team | Not Started
Test | AI Service Accuracy Testing | 8 days | [START_DATE+49] | [START_DATE+57] | A2I Setup | Technical Lead | Not Started
Test | Integration Testing | 7 days | [START_DATE+53] | [START_DATE+60] | Unit Testing | QA Engineer | Not Started
Test | Performance & Load Testing | 5 days | [START_DATE+57] | [START_DATE+62] | Integration Testing | Performance Engineer | Not Started
Test | Security Testing | 5 days | [START_DATE+58] | [START_DATE+63] | Integration Testing | Security Engineer | Not Started
Test | User Acceptance Testing | 7 days | [START_DATE+63] | [START_DATE+70] | Performance Testing | Business Users | Not Started
Deploy | Production Environment Setup | 5 days | [START_DATE+65] | [START_DATE+70] | Security Testing | DevOps Engineer | Not Started
Deploy | Production Validation & Smoke Testing | 3 days | [START_DATE+70] | [START_DATE+73] | Production Environment | QA Lead | Not Started
Deploy | User Training Delivery | 7 days | [START_DATE+66] | [START_DATE+73] | UAT Complete | Training Lead | Not Started
Deploy | Go-Live | 2 days | [START_DATE+73] | [START_DATE+75] | Production Validation | Project Manager | Not Started
Closure | Hypercare Support | 30 days | [START_DATE+75] | [START_DATE+105] | Go-Live | Support Team | Not Started
Closure | Accuracy Monitoring Setup | 5 days | [START_DATE+75] | [START_DATE+80] | Go-Live | Technical Lead | Not Started
Closure | Knowledge Transfer & Documentation | 7 days | [START_DATE+80] | [START_DATE+87] | Go-Live | Project Manager | Not Started
Closure | Project Closure & Lessons Learned | 3 days | [START_DATE+105] | [START_DATE+108] | Hypercare Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | [START_DATE] | Stakeholders aligned; project charter approved; AWS account access confirmed | Project Manager | Not Started
M2 | Discovery Complete | [START_DATE+10] | Document types classified (2-3 types); compliance requirements documented; sample documents collected | Business Analyst | Not Started
M3 | Architecture Approved | [START_DATE+19] | Solution architecture approved; AI services strategy signed off (Textract/Comprehend/A2I); security design validated | Solution Architect | Not Started
M4 | Infrastructure Ready | [START_DATE+26] | AWS infrastructure provisioned; S3 buckets configured; IAM roles created | DevOps Engineer | Not Started
M5 | AI Services Integrated | [START_DATE+49] | Textract/Comprehend/A2I integrated; extraction accuracy targets met (95%+) | Technical Lead | Not Started
M6 | Development Complete | [START_DATE+52] | All APIs functional; processing pipeline operational; monitoring configured | Technical Lead | Not Started
M7 | Testing Complete | [START_DATE+70] | All test phases passed; accuracy >95%; no critical defects; security validated | QA Lead | Not Started
M8 | Go-Live | [START_DATE+75] | Production deployment successful; users trained; monitoring active | Project Manager | Not Started
M9 | Project Closure | [START_DATE+108] | Hypercare complete; knowledge transfer done; lessons learned documented | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | BA | TL | Dev | QA | DevOps | SecArch | Client
Project Charter & Kickoff | A | C | C | I | I | I | I | I | C
Document Classification Requirements | A | C | R | C | I | I | I | I | C
AWS AI Services Assessment | A | R | C | C | I | I | C | C | I
Solution Architecture Design | A | R | C | C | C | I | C | C | I
Security & Compliance Design | A | C | I | C | I | I | I | R | C
Infrastructure Provisioning | A | C | I | C | I | I | R | C | I
Sample Document Collection | A | I | R | I | I | I | I | I | C
Textract/Comprehend Integration | A | C | I | R | C | I | C | I | I
A2I Human Review Setup | A | C | C | R | C | I | I | I | C
API & Pipeline Development | A | C | I | R | R | I | C | I | I
Web Interface Development | A | I | C | C | R | I | I | I | C
Test Planning & Execution | A | I | C | C | C | R | I | C | I
Accuracy Validation | A | C | C | R | C | C | I | I | C
Security Testing | A | I | I | C | I | C | I | R | I
User Acceptance Testing | A | I | C | I | I | C | I | I | R
Production Deployment | A | C | I | C | C | C | R | C | I
User Training | A | I | R | I | I | I | I | I | C
Go-Live Approval | A | C | C | C | C | C | C | C | R
Hypercare Support | A | I | I | C | C | C | R | I | I
Legend:
R | A: Responsible - Does the work
A | A: Accountable - Ultimate ownership
C | A: Consulted - Provides input
I | A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on IDP objectives and AI strategy | Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and major decisions on AI implementation | Project Manager | Alternate Tuesdays
Project Status Meeting | Weekly | Core project team | Review progress and address blockers across all workstreams | Project Manager | Mondays 10:00
Technical Architecture Review | Weekly | Technical leads | AI service design decisions and integration challenges | Solution Architect | Wednesdays 14:00
Development Standup | Daily | Development team | Development progress and coordination | Technical Lead | Daily 09:30
Risk & Issue Review | Bi-weekly | PM and Risk Manager | Risk assessment and mitigation tracking | Risk Manager | Alternate Fridays
QA & Testing Review | Weekly | QA and Development teams | Test progress and accuracy metrics | QA Lead | Thursdays 11:00
Security Review | Bi-weekly | Security team and architects | Security controls and compliance validation | Security Architect | Alternate Wednesdays
Business User Feedback | Weekly | Business stakeholders | Document processing accuracy review and workflow feedback | Business Analyst | Fridays 14:00
Go-Live Readiness | Daily (2 weeks pre) | Go-live team | Deployment preparation and checklist review | Project Manager | Daily 09:00
Post Go-Live Review | Weekly (first month) | Support and operations | Production stability and accuracy monitoring | Support Lead | Mondays 11:00